## Task
# | Task | Description | Assign to | Note | Due | Done?
1 | Website | Fill out an introduction about yourself in Overview > Meet the team | everyone |  | 2022-12-04
2 | Website | Logistic Regression and BNB | Emerald |  | 2022-12-04 | Yes
3 | Website | Our model | Emerald |  | 2022-12-04 | Yes
4 | Website | preprocessing stuff | Emerald |  | 2022-12-04 | Yes
5 | Website | AdaBoost and Random Forest | Anson | Can you break this up into two separate section instead of one? Include the following points: 1. Did you use word embedding? tf-idf or any other text representation techniques? 2. Model's accuracy, precision, recall, f-1 3. Model's confusion matrix Note: I uploaded all the model's performance and confusion matrix in "Single model performances" folder | 2022-12-04
6 | Website | CNN | Lijian | Include the following points: 1. Did you use word embedding? tf-idf or any other text representation techniques? 2. Model's accuracy, precision, recall, f-1 3. Model's confusion matrix Note: I uploaded all the model's performance and confusion matrix in "Single model performances" folder | 2022-12-04
7 | Website | RNN | Garrett | Include the following points: 1. Did you use word embedding? tf-idf or any other text representation techniques? 2. Model's accuracy, precision, recall, f-1 3. Model's confusion matrix Note: I uploaded all the model's performance and confusion matrix in "Single model performances" folder | 2022-12-04
8 | Website | Attention | Garrett | Include the following points: 1. Did you use word embedding? tf-idf or any other text representation techniques? 2. Model's accuracy, precision, recall, f-1 3. Model's confusion matrix Note: I uploaded all the model's performance and confusion matrix in "Single model performances" folder | 2022-12-04
9 | Website | SVC | Jennifer | Include the following points: 1. Did you use word embedding? tf-idf or any other text representation techniques? 2. Model's accuracy, precision, recall, f-1 3. Model's confusion matrix Note: I uploaded all the model's performance and confusion matrix in "Single model performances" folder | 2022-12-04 | Done, 1.I described my answers to these questions on my SVC model section on our website. 2. and 3. I posted the SVC confusion matrix and evaluation table (from Emerald's folder) onto same section on our website
10 | Website | Link github repo to our website | Garrett |  | 2022-12-04
11 | GitHub | Set up github repo with all our code in it | Garrett |  | 2022-12-04
12 | Presentation | Polish up the presentation | Anson, Lijian |  | 2022-12-04
13 | Presentation | Review presentation, website, and github | everyone |  | Dec 10-12

## Sheet1
Oct | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Goals
| 24 | 25 | 26 | 27 | 28 | 29 | 30
|  |  |  | Proposal Due |  |  |  | SVM - Jennifer Bernoulli Naive Bayes - Emerald Logistic Regression - Emerald BERT - Anson CNN - Lijian RNN - Garett Attention - Garett HW5 - Jennifer
Nov | 31 | 1 | 2 | 3 | 4 | 5 | 6
|  |  |  | Model explore HW5 First Draft @3 pm | Meet to pick out top 3 models?
| 7 | 8 | 9 | 10 | 11 | 12 | 13
|  | Finish HW5 |  |  | HW5 due Ensemble due
| 14 | 15 | 16 | 17 | 18 | 19 | 20
Website due
| 21 | 22 | 23 | 24 | 25 | 26 | 27
Dec | 28 | 29 | 30 | 1 | 2 | 3 | 4
| 5 | 6 | 7 | 8 | 9 | 10 | 11
|  |  |  | Final | Presentation | Presentation | Presentation
| 12 | 13 | 14 | 15 | 16 | 17 | 18
| Presentation Day |  | Website and Slides due